## LISEZMOI
Format | ProjMaster WBS Import — v1.0
Généré le | 2026-07-08
Source | ARK_-_Plan_v3.xlsx (feuilles Plan + Actual)
Feuille PROJET | Métadonnées du projet (1 ligne de valeurs).
Feuille RESSOURCES | Référentiel ressources : code, libellé, TJM €. À rapprocher des collaborateurs ProjMaster à l'import.
Feuille WBS | Une ligne = une tâche (feuille de l'arborescence). Hiérarchie via colonnes WBS_L1 (module) et WBS_L2 (catégorie, optionnelle). Dates au format ISO AAAA-MM-JJ. Charges en jours (pas de 0,125).
Feuille REALISE_MENSUEL | Ventilation mensuelle du réalisé : une ligne = tâche × mois. Somme par tâche = Charge_Reelle_j de la feuille WBS.
Statuts | a_faire ¦ en_cours ¦ termine ¦ bloque
Règle | Les cellules vides signifient « non renseigné », jamais zéro.

## PROJET
Cle | Valeur
nom | ARK US — IBM Planning Analytics
client | ARK US
type | BUILD
devise | EUR
date_debut | 2026-03-30
statut_projet | en_cours
source | ARK_-_Plan_v3.xlsx
format_version | 1.0

## RESSOURCES
Code | Libelle | Profil | TJM_EUR | Facturable
DTc | DATATILT — Consultant | C | 900 | OUI
DTe | DATATILT — Expert | E | 1150 | OUI
DTt | DATATILT — Expert Training | T | 2000 | OUI
ARK | ARK US — Équipe client |  | 0 | NON

## WBS
ID | WBS_L1 | WBS_L2 | Tache | Commentaire | Ressource | Statut | Charge_Prevue_j | Charge_Planifiee_j | Charge_Reelle_j | Cout_Prevu_EUR | Debut_Prev | Fin_Prev | Debut_Reel | Fin_Reel | Prerequis
T001 | KickOff & Modélisation | Modele | KickOff & Modélisation | Moderlisation Orga | DTc | termine | 1 | 1 | 0.75 | 900 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | YES
T002 | Module 1: PL US | Refrential | AREA.dim | Script Create Dimension | DTc | termine | 0.125 | 0.125 | 0.25 | 112.5 | 2026-03-31 | 2026-03-31 | 2026-03-30 | 2026-03-30 | YES
T003 | Module 1: PL US | Refrential | CONTRACT.dim | Script Create Dimension | DTc | termine | 0.125 | 0.125 | 0.125 | 112.5 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | YES
T004 | Module 1: PL US | Refrential | DEPARTEMENT.dim | Script Create Dimension | DTc | termine | 0.5 | 0.5 | 0.5 | 450 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | YES
T005 | Module 1: PL US | Refrential | MODEL.dim | Script Create Dimension | DTc | termine | 0.125 | 0.125 | 0.125 | 112.5 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | YES
T006 | Module 1: PL US | Refrential | TYPE_LICENCE.dim | Script Create Dimension | DTc | termine | 0.125 | 0.125 | 0.125 | 112.5 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | YES
T007 | Module 1: PL US | Refrential | ENTITY.dim | Script Create Dimension | DTc | termine | 0.125 | 0.125 | 0.125 | 112.5 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-03-31 | YES
T008 | Module 1: PL US | Refrential | Managing organizational change 'Entitiy , Departement) | Script if we change a dept to ancestors and child | DTc | termine | 1.5 | 1.5 | 1.25 | 1350 | 2026-04-01 | 2026-04-02 | 2026-04-09 | 2026-04-10 | YES
T009 | Module 1: PL US | Refrential | PL_ACCOUNT.dim | Script Create Dimension | DTc | termine | 1 | 1 | 0.25 | 900 | 2026-04-03 | 2026-04-03 | 2026-04-01 | 2026-04-02 | YES
T010 | Module 1: PL US | Cube | PL_US.cub | Script Create Cube | DTc | termine | 0.25 | 0.25 | 0.25 | 225 | 2026-04-07 | 2026-04-07 | 2026-04-01 | 2026-04-01 | YES
T011 | Module 1: PL US | Script | Script load MAPPING PL ACCOUNT & Out NS. | Load cube from NetSuite file | DTc | termine | 0.5 | 0.5 | 1.125 | 450 | 2026-04-07 | 2026-04-07 | 2026-04-01 | 2026-04-08 | YES
T012 | Module 1: PL US | Script | Script load data | Load cube from NetSuite file | DTc | termine | 1.5 | 1.5 | 2.375 | 1350 | 2026-04-08 | 2026-04-09 | 2026-04-01 | 2026-04-16 | YES
T013 | Module 1: PL US | Screen | Administration console | Managing the dimension updates and PL Loading | DTc | termine | 1 | 0.5 | 1.75 | 900 | 2026-04-09 | 2026-04-09 | 2026-04-07 | 2026-04-08 | YES
T014 | Module 1: PL US | Script | Security US | Script Manage Security | DTc | termine | 1 | 1 | 0.25 | 900 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | Not YET
T015 | Module 1: PL US | UAT | Test | 0.15 | DTc | a_faire | 1.1812 | 1 | 1.125 | 1063.12 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14
T016 | Module 1: PL US | Support | Support Post Delivery |  | DTc | a_faire | 1 | 1 | 0.75 | 900 | 2026-04-15 | 2026-04-20 | 2026-04-16 | 2026-04-23
T017 | Module 1: PL US | Support | To be test by US |  | ARK | a_faire | 4 | 4 | 4 |  | 2026-04-15 | 2026-04-20 | 2026-04-20 | 2026-04-23
T018 | Module 2 GROUP Conco | Cube | Conso Cube | Script Load Data | DTc | en_cours | 2 | 2 | 3 | 1800 | 2026-04-14 | 2026-04-16 | 2026-04-15 | 2026-04-24 | YES
T019 | Module 2 GROUP Conco | Refrential | Region.dim | Script Create Dimension | DTc | termine | 0.125 | 0.125 |  | 112.5 | 2026-04-17 | 2026-04-17 |  |  | ToBeConf
T020 | Module 2 GROUP Conco | Refrential | TYPE_EXPENSES.dim | Script Create Dimension | DTc | bloque | 0.125 | 0.125 |  | 112.5 | 2026-04-17 | 2026-04-17 |  |  | ToBeConf
T021 | Module 2 GROUP Conco | Refrential | Phase.dim | Script Create Dimension | DTc | termine | 0.125 | 0.125 |  | 112.5 | 2026-04-17 | 2026-04-17 |  |  | ToBeConf
T022 | Module 2 GROUP Conco | Refrential | Business Line.dim | Script Create Dimension | DTc | bloque | 0.125 | 0.125 |  | 112.5 | 2026-04-17 | 2026-04-17 |  |  | ToBeConf
T023 | Module 2 GROUP Conco | Script | Lock/ Unlock Conso | Admin Console to lock and unlock the data copy from Region to Conso | DTc | termine | 1.5 | 1.5 | 1.5 | 1350 | 2026-04-17 | 2026-04-21 | 2026-04-20 | 2026-04-24 | YES
T024 | Module 2 GROUP Conco | Report | Report: PL Report (onglet P&L) | Create Reports: Checks if all accounts exist ! | DTc | a_faire | 1 | 1 | 1.5 | 900 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-30 | ToBeConf
T025 | Module 2 GROUP Conco | Report | Report: PL Report - Services Focus | Create Reports | DTc | a_faire | 1 | 1 | 0.75 | 900 | 2026-04-23 | 2026-04-23 | 2026-04-28 | 2026-04-29 | ToBeConf
T026 | Module 2 GROUP Conco | Report | Report: Focus ADSK | Create Reports: Need specifications | DTc | a_faire | 1.5 | 1.5 | 0.75 | 1350 | 2026-04-24 | 2026-04-27 | 2026-04-29 | 2026-04-30 | Not YET
T027 | Module 2 GROUP Conco | UAT | Test | 0.15 | DTc | a_faire | 1.125 | 1 | 0.5 | 1012.5 | 2026-04-27 | 2026-04-28 | 2026-05-05 | 2026-05-05
T028 | Module 2 GROUP Conco | Support | Module 2 GROUP Conco |  | DTc | a_faire | 1 | 1 |  | 900 | 2026-05-06 | 2026-05-11
T029 | Module 2 GROUP Conco | Delivery | To be test by US |  | ARK | a_faire | 3 | 3 | 3 |  | 2026-05-06 | 2026-05-11 | 2026-05-06 | 2026-05-11
T030 | Module 3 Production Delivery |  | Feedback Support |  | DTc | a_faire | 3 | 3 |  | 2700 | 2026-05-12 | 2026-05-18
T031 | Module 3 Production Delivery |  | Prod Delivery |  | DTc | a_faire | 1 | 1 |  | 900 | 2026-05-20 | 2026-05-20
T032 | Module 3 Production Delivery |  | Support Post Prod |  | DTc | a_faire | 5 |  |  | 4500
T033 | Documentation |  | Documentation | 0.1 | DTc | a_faire | 3.5 | 3 | 1 | 3150 | 2026-05-21 | 2026-05-25 | 2026-05-18 | 2026-05-25
T034 | Training IBM PA |  | Training IBM Planning Analytics - User |  | DTt | a_faire | 2 | 2 | 4 | 4000 | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-06-05
T035 | PM |  | PM | 0.1 | DTe | a_faire | 4 |  | 2 | 4600 |  |  | 2026-03-30 | 2026-05-25
T036 | Module 2 GROUP Conco | Refrential | Dimension Creation | Create all dimensions of consolidated cube | DTc | termine | 0.5 |  | 1.375 | 450 |  |  | 2026-04-14 | 2026-04-24
T037 | Module 2 GROUP Conco | Book | Administration book for PL group | Create administration book for PL group | DTc | en_cours |  |  | 1 |  |  |  | 2026-04-21 | 2026-04-22
T038 | Module 2 GROUP Conco | Script | Rework |  | DTc | a_faire | 2 |  | 2.5 | 1800 |  |  | 2026-04-24 | 2026-05-18

## REALISE_MENSUEL
ID_Tache | Tache | Mois | Jours
T001 | KickOff & Modélisation | 2026-03 | 0.75
T002 | AREA.dim | 2026-03 | 0.25
T003 | CONTRACT.dim | 2026-03 | 0.125
T004 | DEPARTEMENT.dim | 2026-03 | 0.5
T005 | MODEL.dim | 2026-03 | 0.125
T006 | TYPE_LICENCE.dim | 2026-03 | 0.125
T007 | ENTITY.dim | 2026-03 | 0.125
T008 | Managing organizational change 'Entitiy , Departement) | 2026-04 | 1.25
T009 | PL_ACCOUNT.dim | 2026-04 | 0.25
T010 | PL_US.cub | 2026-04 | 0.25
T011 | Script load MAPPING PL ACCOUNT & Out NS. | 2026-04 | 1.125
T012 | Script load data | 2026-04 | 2.375
T013 | Administration console | 2026-04 | 1.75
T014 | Security US | 2026-04 | 0.25
T015 | Test | 2026-04 | 1.125
T016 | Support Post Delivery | 2026-04 | 0.75
T017 | To be test by US | 2026-04 | 4
T018 | Conso Cube | 2026-04 | 3
T023 | Lock/ Unlock Conso | 2026-04 | 1.5
T024 | Report: PL Report (onglet P&L) | 2026-04 | 1.5
T025 | Report: PL Report - Services Focus | 2026-04 | 0.75
T026 | Report: Focus ADSK | 2026-04 | 0.75
T027 | Test | 2026-05 | 0.5
T029 | To be test by US | 2026-05 | 3
T033 | Documentation | 2026-05 | 1
T034 | Training IBM Planning Analytics - User | 2026-04 | 2
T034 | Training IBM Planning Analytics - User | 2026-06 | 2
T035 | PM | 2026-03 | 1
T035 | PM | 2026-04 | 0.5
T035 | PM | 2026-05 | 0.5
T036 | Dimension Creation | 2026-04 | 1.375
T037 | Administration book for PL group | 2026-04 | 1
T038 | Rework | 2026-04 | 2
T038 | Rework | 2026-05 | 0.5